POP TELECOM

Broadband Buddy Product Availability Integration

Clarification and Sign-off Form

| Document purpose | Capture all open decisions, confirmations, and scoping answers required before the BB integration build begins |
| --- | --- |
| Scope spec ref | BB Product Availability Scope Spec v1.2 |
| Developer response ref | POP Tel BB Developer Response v1.1 |
| Date | March 2026 |
| Completed by |  |
| Date completed |  |
| Reviewed by |  |

|  | How to use this form Work through each section in order. For each question, circle or mark your chosen option, tick applicable checkboxes, and write your answer in the blank fields. Questions marked BLOCKER must be answered before any build estimate is produced. Return the completed form to Sam / maastrix before the architecture meeting. |
| --- | --- |

| BLOCKER | REQUIRED | TBC | Action: JB | Arch meeting |  |
| --- | --- | --- | --- | --- | --- |

Legend: BLOCKER = build cannot start without this answer.  REQUIRED = needed before estimation.  TBC = needs decision.  Action: JB = JB to provide.  Arch meeting = confirm at architecture meeting.

01  Architecture Decisions

Structural decisions that must be locked before any build work or estimation begins. These affect cost, build order, and what gets built.

| A1 BLOCKER. | Does a separate adapter service sit between POP Telecom and Broadband Buddy, or does POP call BB directly? The scope spec leaves this open. It affects the estimate and what gets built. The two options below have different build costs. Must be agreed at the architecture meeting before integration work starts. |
| --- | --- |

|  | Why it matters If a separate adapter is built, that is an additional build item with its own estimate. If POP calls BB directly, auth and request translation must be handled inside BB. Either way the decision changes what maastrix needs to build. |
| --- | --- |

| A | POP Telecom calls the Broadband Buddy API directly. BB handles auth and request validation internally. No separate service. Lower build cost. Simpler architecture. Less control over auth at the POP level. |
| --- | --- |

| B | A thin adapter service sits between POP and BB. Handles auth, request translation, and response normalisation. Additional build item. More control. Useful if POP and BB use different auth models. |
| --- | --- |

Decision rationale and any conditions attached

| A2 BLOCKER. | Who performs the postcode and address resolution — POP Telecom or Broadband Buddy? The flow diagram shows POP performing an ALK/CSS district code lookup before calling BB. The client Q&A suggests passing postcode and door number directly to BB for it to handle. These produce different build items. |
| --- | --- |

|  | Also needed Regardless of which option is chosen, the exact field payload — field names, format, whether door number is sent separately — must be agreed and documented in the API contract before the integration build starts. |
| --- | --- |

| A | POP performs the ALK/CSS district code lookup first, then sends the resolved code to BB. POP needs access to the lookup service. More logic sits in POP. |
| --- | --- |

| B | POP sends raw postcode + selected address to BB. BB handles district code resolution internally. Simpler POP side. BB must handle all address resolution. |
| --- | --- |

Agreed field payload format (field names, types, structure)

Notes / confirm with BB team before build starts

| A3 REQUIRED. | Confirm: POP Telecom Laravel backend is being extended, not rebuilt. The spec confirms: extend, not rebuild. Full rebuild was estimated at ~30 weeks. BB integration approach targets ~10 weeks. Recorded here for formal sign-off. |
| --- | --- |

| A | Confirmed — extend existing Laravel backend only. No rebuild in Stage 1 or Stage 2. |
| --- | --- |

| B | Change of direction — partial or full rebuild is now under consideration. If selected, describe scope and revised timeline implications below. |
| --- | --- |

Notes / caveats

02  Stage 1 — Availability

Stage 1 covers availability checking only. No ordering, no payment, no AKJ. These questions define what gets built and what the sign-off criteria are.

| B1 REQUIRED. | Which suppliers are in scope for Stage 1 availability checks? PXC is already working in BB. Freedom Fibre and Giacom need to be added. Confirm what is in scope for Stage 1 so the estimate reflects only confirmed suppliers. |
| --- | --- |

|  | PXC — already integrated in BB. Includes CityFibre (CFH) results. In scope for Stage 1. |
| --- | --- |

|  | Giacom — to be added to BB in Stage 1. Requires API credentials and integration work. |
| --- | --- |

|  | Freedom Fibre — to be added to BB in Stage 1. Requires API credentials and integration work. |
| --- | --- |

Suppliers NOT in Stage 1 and reason (e.g. API access not yet confirmed)

| B2 REQUIRED. | What does POP Telecom display when Broadband Buddy is unavailable or returns an error? BB unavailability handling must be explicitly built and tested on the POP side. POP must not show partial results, cached data, or a blank page with no explanation. |
| --- | --- |

|  | Spec requirement If BB is unavailable, POP Telecom must display a fallback message and prevent product display rather than showing incomplete or cached results. This behaviour needs to be explicitly built and tested. |
| --- | --- |

| A | Show a clear user-facing error message and prevent product display entirely. No cached data shown. |
| --- | --- |

| B | Show a user-facing error message but fall back to the existing direct API flow as a temporary backup. More complex to build. Requires the old flow to remain active in parallel during transition. |
| --- | --- |

| C | Other — define below. |
| --- | --- |

Agreed fallback message text (exact wording for the customer to see)

| B3 REQUIRED. | What are the Stage 1 sign-off criteria? What does 'Stage 1 stable' mean? Stage 2 cannot go live until Stage 1 is complete and stable. Tick the criteria that must be met before Stage 2 begins. |
| --- | --- |

|  | BB availability endpoint live and returning results across all in-scope suppliers |
| --- | --- |

|  | POP catalogue mapping working — BB catalogueName correctly matches to internal POP product record |
| --- | --- |

|  | Product display signed off by JB on staging — pricing and content correct |
| --- | --- |

|  | BB unavailability fallback built and tested |
| --- | --- |

|  | Priority and deduplication logic confirmed — no duplicate products shown to customer |
| --- | --- |

|  | All in-scope suppliers returning results in test environment |
| --- | --- |

|  | Response contract agreed and documented between BB and POP dev teams |
| --- | --- |

Additional sign-off criteria specific to POP Telecom

03  Stage 2 — Ordering

Stage 2 adds order placement, Order ID handling, and AKJ integration. Stage 1 must be complete and stable before Stage 2 goes live. Stage 2 can be estimated in parallel with Stage 1 delivery.

| C1 REQUIRED. | Confirm the order placement sequence — customer selects, pays, then POP sends to BB. The working assumption for estimation is that payment is taken by POP before the order is sent to BB. Tick each step to confirm the sequence is correct. |
| --- | --- |

|  | Working assumption Payment stays in POP. BB only receives the order after POP confirms payment. BB has no involvement in payment at any point. This is the estimation baseline and has not been formally closed in the base spec. |
| --- | --- |

|  | 1. Customer selects product on POP Telecom site |
| --- | --- |

|  | 2. POP applies pricing from its internal product catalogue |
| --- | --- |

|  | 3. Customer pays via the existing POP payment gateway |
| --- | --- |

|  | 4. POP sends order to BB only after payment is confirmed |
| --- | --- |

|  | 5. BB determines correct supplier using priority rules and product matching |
| --- | --- |

|  | 6. BB places order with supplier API |
| --- | --- |

|  | 7. Supplier confirms and returns Order ID |
| --- | --- |

|  | 8. BB stores Order ID and returns it to POP |
| --- | --- |

|  | 9. POP stores Order ID against the customer order record |
| --- | --- |

|  | 10. POP writes Order ID to the corresponding AKJ task notes |
| --- | --- |

Any deviations from the above sequence

| C2 BLOCKER. | What happens if the order fails at the supplier after payment has already been taken? Payment is collected by POP before the order is sent to BB. If BB or the supplier rejects the order after that point, there is a customer with a pending charge and no order. This is not defined in the current spec. |
| --- | --- |

|  | Risk This must be answered before Stage 2 goes live. If not handled, there is a real risk of taking payment from a customer without fulfilling the order. |
| --- | --- |

| A | POP automatically refunds the customer and creates a support task in AKJ. |
| --- | --- |

| B | POP flags the order as failed, holds payment, and notifies the team manually to investigate and resolve. |
| --- | --- |

| C | Other — define the exact failure handling behaviour below. |
| --- | --- |

Failure handling behaviour — what POP does, what the customer sees, what the team is notified

| C3 TBC. | What is the mechanism for writing the Order ID to the AKJ task? AKJ task note write is in Stage 2 scope in principle. The AKJ Task ID is already stored in the POP backend. The exact technical mechanism has not been confirmed. |
| --- | --- |

| A | POP calls the AKJ API directly with the Order ID and note text after order confirmation. |
| --- | --- |

| B | AKJ is updated via a webhook that BB triggers after the supplier confirms the order. |
| --- | --- |

| C | Manual process — team updates AKJ manually using the Order ID from the POP order record. |
| --- | --- |

| Is the AKJ API available for POP to call? Yes — API available and documented. No — manual or other method required. Not confirmed yet. | AKJ API documentation / auth details if known |
| --- | --- |

| C4 TBC. | Is post-order status sync in Stage 2 scope or deferred? As an order progresses through the supplier network the status will change. Those changes may need to trigger updates to AKJ task due dates and notes. Marked TBA in the spec. |
| --- | --- |

| A | In Stage 2 scope — status changes from supplier must trigger AKJ task updates. Include in Stage 2 estimate. |
| --- | --- |

| B | Deferred — not in Stage 2. Order ID and initial note written only. Status sync scoped in a later phase. |
| --- | --- |

If in Stage 2 scope — what triggers the update and what changes in AKJ (due date, note text, status field)

04  Product Catalogue

POP Telecom owns the internal product catalogue. BB returns a catalogueName and POP maps it to an internal record with its own pricing and display data.

| D1 BLOCKER. | Has JB produced the product equivalence mapping sheet? This sheet maps equivalent products across Freedom Fibre, Giacom, and PXC portals. It is a hard blocker on the critical path. BB availability engine build cannot start without it. |
| --- | --- |

|  | Critical path note Product mapping sheet is the first item on the critical path: mapping sheet → BB availability engine → POP integration → frontend display. A delay here delays everything downstream. |
| --- | --- |

| A | Completed — mapping sheet is ready and can be shared with the dev team immediately. |
| --- | --- |

| B | In progress — JB is working on it. Expected completion date below. |
| --- | --- |

| C | Not started — needs to be made the immediate priority before any build begins. |
| --- | --- |

| Expected completion date | Link or location of mapping sheet |
| --- | --- |

| D2 TBC. | Two types of matching — confirm you understand the difference. BB matching and POP catalogue mapping are two separate steps. Both must be built correctly. They are not the same thing. |
| --- | --- |

|  | Important distinction BB matching decides whether supplier products are equivalent across suppliers and which one to show based on priority. POP mapping decides which internal POP product record corresponds to the catalogue name BB returns, and what price and description to display. These are two separate steps built in two different systems. |
| --- | --- |

|  | Understood — BB matching is handled in Broadband Buddy (deduplication and priority). |
| --- | --- |

|  | Understood — POP catalogue mapping is handled in POP Telecom (catalogueName to internal record). |
| --- | --- |

|  | Understood — both must be in place before products display correctly on the site. |
| --- | --- |

Questions or clarifications on the matching logic

| D3 Action: JB. | Who is responsible for maintaining the catalogue mapping when suppliers add new products? When BB returns a catalogueName that has no matching record in POP, that product will not display. A maintenance process is needed. |
| --- | --- |

| A | JB manages the mapping. New products are added to POP catalogue manually when notified by BB or the supplier. |
| --- | --- |

| B | BB notifies POP via an agreed process (email, Trello card, or notification) when new products are available. |
| --- | --- |

| C | POP admin UI surfaces unmatched products for JB to map without needing to contact the dev team. |
| --- | --- |

Define the maintenance process and who owns it long term

| D4 Action: JB. | Has the dynamic product content template been defined for the product display page? JB must supply the product page template with field mappings before the frontend display build starts. Tick the fields that have been confirmed. |
| --- | --- |

|  | Product name |
| --- | --- |

|  | Technology type (FTTP / SoGEA) |
| --- | --- |

|  | Download and upload speeds |
| --- | --- |

|  | Monthly price |
| --- | --- |

|  | Upfront cost |
| --- | --- |

|  | Contract length |
| --- | --- |

|  | CPI / annual increase terms |
| --- | --- |

|  | Add-on display (if applicable at this stage) |
| --- | --- |

Status of template and link / location if available

05  Suppliers and Priority

Priority rules and supplier configuration live in Broadband Buddy. POP Telecom consumes the results. These questions confirm the setup and any outstanding supplier commercial decisions.

| E1 REQUIRED. | Confirm supplier priority order: Freedom Fibre (1), Giacom (2), PXC (3). This is the order BB uses to decide which supplier to show and route orders to when the same product is available from more than one supplier. |
| --- | --- |

| A | Confirmed — Freedom Fibre first, Giacom second, PXC third. |
| --- | --- |

| B | Priority order needs to change — define correct order and reason below. |
| --- | --- |

If changed — new priority order and reason

| E2 TBC. | Where does the supplier priority admin interface live — BB admin only, or also in POP Telecom? Priority rules must be configurable without code changes. BB owns all supplier logic so the natural home is BB admin. Whether POP exposes a control surface is still to be confirmed. |
| --- | --- |

| A | BB admin only — POP team logs into BB admin to change priority. POP site has no control panel for this. |
| --- | --- |

| B | Both — BB admin is source of truth, but POP also exposes a simplified control surface for priority management. |
| --- | --- |

Who needs access to change priority and how often is it expected to change

| E3 TBC. | Current status of CityFibre routing via Freedom Fibre or Giacom. PXC currently returns CityFibre (CFH) availability. Commercial deals with Freedom Fibre and Giacom for direct CF routing are in progress. Update below. |
| --- | --- |

| A | CityFibre continues via PXC for now. No change to current setup at Stage 1. |
| --- | --- |

| B | Deal confirmed with Freedom Fibre or Giacom for CF routing — update priority rules accordingly. |
| --- | --- |

| C | Still in negotiation — proceed on assumption of PXC routing for Stage 1. |
| --- | --- |

Deal status update — G Networks, Freedom Fibre, Giacom

| E4 REQUIRED. | Confirm supplier API credentials are available for Freedom Fibre and Giacom. The BB availability engine build for Freedom Fibre and Giacom requires API credentials before work can start. PXC credentials are already in place. |
| --- | --- |

|  | PXC API credentials in place Already working in BB. |
| --- | --- |

|  | Giacom API credentials confirmed and available to pass to maastrix |
| --- | --- |

|  | Freedom Fibre API credentials confirmed and available to pass to maastrix |
| --- | --- |

If not available — expected date and who is obtaining them

06  Payment and Pricing

Payment and pricing stay entirely in POP Telecom. BB has no involvement. These questions confirm the working assumptions so the estimate is based on correct information.

| F1 REQUIRED. | Confirm the existing POP payment gateway is used unchanged for Stage 1 and Stage 2. Working assumption: payment stays in POP using the existing gateway. BB is not expected to handle payment at any point in Stage 1 or Stage 2. |
| --- | --- |

| A | Confirmed — existing POP payment gateway, no changes required. |
| --- | --- |

| B | Change required — a different or updated payment method is needed. If selected, describe below. |
| --- | --- |

| Current payment provider / gateway name | Any payment-related changes planned alongside this integration |
| --- | --- |

| F2 REQUIRED. | Confirm all pricing — monthly, upfront, CPI — comes from the POP internal catalogue, not from BB. BB returns catalogue name and speed only. Pricing is derived entirely from the matched internal POP product record. The developer draft incorrectly assumed pricing was lost. It is not. |
| --- | --- |

| A | Confirmed — all pricing from POP internal catalogue. BB returns no pricing data. |
| --- | --- |

| B | Some pricing data will come from the supplier via BB. Define which pricing fields and why below. |
| --- | --- |

Pricing edge cases or any fields not covered by the internal catalogue

07  Routers and Add-ons

Routers and add-ons are deferred from BB integration scope. The existing POP logic does not need to be dismantled. These questions confirm the estimation default and whether any exceptions apply.

| G1 Action: JB. | For Stage 1 and Stage 2 estimation, confirm routers and add-ons are excluded from BB integration scope. Estimation default: routers and add-ons excluded unless JB confirms otherwise. Existing POP logic stays in place. BB does not support routers or add-ons and this is not expected of it. |
| --- | --- |

| A | Confirmed — excluded from Stage 1 and Stage 2. Existing POP logic untouched. To be scoped in a later phase. |
| --- | --- |

| B | Partial inclusion required — some router or add-on logic must be in Stage 1 or Stage 2. If selected, define exactly what and in which stage below. |
| --- | --- |

If partial inclusion — what specifically and in which stage

| G2 Action: JB. | When a customer buys via the new BB availability flow, can they still select a router and add-ons from the existing POP catalogue independently? If yes, the checkout UX must show product selection (from BB) and router/add-on selection (from POP) as separate steps in the same flow. |
| --- | --- |

| A | Yes — router and add-on selection remains as a separate independent step in the POP checkout flow. |
| --- | --- |

| B | No — router and add-on selection is suspended for Stage 1 and Stage 2. To be reintroduced later. |
| --- | --- |

| C | Not decided yet — JB to confirm before frontend build starts. |
| --- | --- |

UX notes or any business logic that affects how routers/add-ons interact with the new flow

08  AKJ and Order Integration

AKJ is the billing and task management system. The AKJ Task ID is already stored in POP Telecom. Order ID must be written to AKJ at order time. These questions confirm the integration approach.

| H1 REQUIRED. | Confirm the AKJ Task ID is currently stored in the POP Telecom database against each customer or order record. Stated in the spec as already in place. Confirmation needed so devs do not have to build this step. |
| --- | --- |

| A | Confirmed — AKJ Task ID is stored in the POP database. Field name and location are known. |
| --- | --- |

| B | Partially confirmed — stored for some records but not all. Needs investigation. |
| --- | --- |

| C | Not confirmed — needs to be checked before Stage 2 estimate is produced. |
| --- | --- |

| Database table and field name where AKJ Task ID is stored e.g. orders.akj_task_id. | Is the AKJ Task ID present on all order records or only some? |
| --- | --- |

| H2 Action: JB. | What note text should be appended to the AKJ task when an Order ID is received? POP writes to the AKJ task notes. The exact text format must be agreed so devs can implement it without guessing. |
| --- | --- |

Agreed note format or template (include all fields to be shown — Order ID, supplier, product, date etc.)

Any other information to include in the AKJ task note

09  CRM and Data Centralisation

CRM integration is deferred from Stage 1 and Stage 2. The current build must not create point-to-point data coupling that would block a future CRM phase.

| I1 TBC. | Confirm CRM integration is deferred and not in Stage 1 or Stage 2 scope. Zoho vs custom CRM remains unresolved. The integration proceeds without CRM dependency. Decision needed before the data centralisation phase begins. |
| --- | --- |

| A | Confirmed — CRM deferred. No CRM dependency in Stage 1 or Stage 2. Build proceeds as planned. |
| --- | --- |

| B | CRM decision has been made — define which CRM and whether it needs to be included in this phase. |
| --- | --- |

If CRM decided — which system and what integration is required

| I2 TBC. | Is there any requirement to export or centralise customer or order data during Stage 1 or Stage 2? Even without a CRM decision, there may be a need to consolidate data from POP, BB, and AKJ for reporting or operations. Flag any such requirement here. |
| --- | --- |

| A | No — data stays in each system. No centralisation needed in Stage 1 or Stage 2. |
| --- | --- |

| B | Yes — there is a reporting or operational need. Define below. |
| --- | --- |

Data export, reporting, or cross-system visibility requirements

10  API Contract and Technical Handshake

Before the POP Telecom integration build starts, the BB team must agree and document the response format. Any change to this format after build begins will break the integration.

| J1 REQUIRED. | Has BB produced a documented API response schema for the availability endpoint? The response format BB returns to POP must be treated as a versioned contract. POP dev team must see this before they build the integration layer. |
| --- | --- |

|  | Spec requirement Broadband Buddy response format must be treated as a contract and versioned to avoid breaking the POP Telecom integration. BB must version its API responses and communicate breaking changes to the POP dev team before deploying them. |
| --- | --- |

| A | Yes — API schema is documented and ready to share with the POP dev team. |
| --- | --- |

| B | In progress — BB team is working on it. Expected completion below. |
| --- | --- |

| C | Not yet — needs to be produced before POP integration build starts. |
| --- | --- |

Link to API schema / documentation

Confirm the availability response includes the following fields. Tick each one:

|  | catalogueName — the product identifier that POP maps to its internal catalogue |
| --- | --- |

|  | speed — download / upload speed |
| --- | --- |

|  | technology — FTTP or SoGEA |
| --- | --- |

|  | supplier — which supplier this result comes from |
| --- | --- |

|  | priority — the priority rank assigned by BB |
| --- | --- |

Any additional fields in the response, or fields with different names

| J2 REQUIRED. | Has BB agreed a process for communicating breaking API changes before deployment? If BB changes a field name or structure without notice, the POP integration will break silently. A communication process must be agreed. |
| --- | --- |

| A | Yes — BB will version the API and notify POP dev team before deploying any breaking changes. |
| --- | --- |

| B | Not yet agreed — needs to be confirmed as part of the architecture meeting. |
| --- | --- |

Agreed process for API change communication (who tells who, how much notice, how changes are flagged)

11  Sign-off Tracker

Use this section to record who signed off each area. All BLOCKER items must be signed off before build begins.

| Ref | Question summary | Answered by | Date | Signed off |
| --- | --- | --- | --- | --- |
| A1 | Adapter service decision |  |  |  |
| A2 | Postcode lookup ownership |  |  |  |
| A3 | Backend extend vs rebuild |  |  |  |
| B1 | Stage 1 suppliers in scope |  |  |  |
| B2 | BB fallback behaviour |  |  |  |
| B3 | Stage 1 sign-off criteria |  |  |  |
| C1 | Order placement sequence |  |  |  |
| C2 | Order failure after payment |  |  |  |
| C3 | AKJ write mechanism |  |  |  |
| C4 | Order status sync scope |  |  |  |
| D1 | Product mapping sheet |  |  |  |
| D2 | BB vs POP matching distinction |  |  |  |
| D3 | Catalogue mapping maintenance |  |  |  |
| D4 | Product content template |  |  |  |
| E1 | Supplier priority confirmed |  |  |  |
| E2 | Priority admin interface |  |  |  |
| E3 | CityFibre routing status |  |  |  |
| E4 | Supplier API credentials |  |  |  |
| F1 | Payment gateway confirmed |  |  |  |
| F2 | Pricing from POP catalogue only |  |  |  |
| G1 | Routers/add-ons excluded |  |  |  |
| G2 | Router selection in checkout |  |  |  |
| H1 | AKJ Task ID in POP DB |  |  |  |
| H2 | AKJ note text format |  |  |  |
| I1 | CRM deferred |  |  |  |
| I2 | Data centralisation requirement |  |  |  |
| J1 | BB API schema documented |  |  |  |
| J2 | API change communication agreed |  |  |  |

|  | Note on blockers Questions A1, A2, C2, and D1 are marked as blockers. Build cannot begin until these four are answered. All other REQUIRED items must be answered before a final estimate is produced. |
| --- | --- |

End of Form

POP Telecom x Broadband Buddy Product Availability Integration  |  Clarification Form v1.0  |  March 2026